Capstone Project Report

Report 2 – Project Management Plan

– Can Tho, August 2023 –

Table of Contents

I. Project Report	3

Team Involvements	3

II. Project Management Plan	3

1. Overview	3

1.1 WBS & Estimation	3

1.2 Project Risks	11

2. Management Approach	11

2.1 Project Process	11

2.2 Quality Management	12

2.3 Training Plan	12

3. Master Schedule	13

4. Responsibility Assignments	15

5. Project Communication	16

6. Configuration Management	17

6.1 Tools & Infrastructures	17

6.2 Document Management	17

6.3 Source Code Management	17

# I. Project Report

## Team Involvements

| # | Task | Member | Notes (Task Details, etc.) |
| --- | --- | --- | --- |
|  | Overview | TinTT |  |
|  | Management Approach | HungLH |  |
|  | Master Schedule | HieuTH |  |
|  | Responsibility Assignments | KhangLTV |  |
|  | Project Communication | KhangLTV |  |
|  | Configuration Management | KhaTM |  |

# II. Project Management Plan

## 1. Overview

### 1.1 WBS & Estimation

| # | WBS Item | Complexity | Est. Effort |
| --- | --- | --- | --- |
|  |  |  | (man-days) |
| 1 | Scan AI detection acne |  |  |
| 1. 1 | Searching for datasets | Medium | 1 |
| 1. 2 | Research the AI train model | Medium | 1 |
| 1. 3 | Research AI training algorithm | Complex | 3 |
| 1. 4 | Training model | Complex | 3 |
| 2 | Create android application UI |  |  |
| 2. 1 | Design login screen | Medium | 0.1 |
| 2. 2 | Design register screen | Medium | 0.1 |
| 2. 3 | Design register email verify screen | Simple | 0.1 |
| 2. 4 | Design forgot password screen | Medium | 0.1 |
| 2. 5 | Design home screen | Complex | 0.1 |
| 2. 6 | Design medical record screen | Medium | 0.1 |
| 2. 7 | Design invoice screen | Complex | 0.1 |
| 2. 8 | Design detail invoice screen | Medium | 0.1 |
| 2. 9 | Design services list | Medium | 0.1 |
| 2. 10 | Design appointment screen | Medium | 0.1 |
| 2. 11 | Design appointment list screen | Medium | 0.1 |
| 2. 12 | Design appointment detail screen | Medium | 0.1 |
| 2. 13 | Design list of acne screen | Simple | 0.1 |
| 2. 14 | Design detailed information of acne screen | Medium | 0.1 |
| 2. 15 | Design list cause of acne screen | Simple | 0.1 |
| 2. 16 | Design detailed information cause of acne screen | Medium | 0.1 |
| 2. 17 | Design list of acne prevention measures screen | Simple | 0.1 |
| 2. 18 | Design detailed information acne prevention measures screen | Simple | 0.1 |
| 2. 19 | Design scan AI detection acne screen | Simple | 0.1 |
| 2. 20 | Design profile user screen | Simple | 0.1 |
| 2. 21 | Design edit profile user screen | Simple | 0.1 |
| 2. 22 | Design the home screen of the role doctor | Complex | 0.1 |
| 2. 23 | Design the appointment screen of the role doctor | Simple | 0.1 |
| 2. 24 | Design the appointment detail screen of the role doctor | Simple | 0.1 |
| 2. 25 | Design the medical record screen of the role doctor | Simple | 0.1 |
| 2. 26 | Design the patient examined screen of the role doctor | Simple | 0.1 |
| 3 | Create web-based application UI |  |  |
| 3. 1 | Design home page | Complex | 0.5 |
| 3. 2 | Design login page | Simple | 0.1 |
| 3. 3 | Design register page | Simple | 0.1 |
| 3. 4 | Design forgot password page | Simple | 0.1 |
| 3. 5 | Design appointment page | Complex | 0.1 |
| 3. 6 | Design list of appointment page | Simple | 0.1 |
| 3. 7 | Design profile page | Medium | 0.1 |
| 3. 8 | Design medical report page | Medium | 0.1 |
| 3. 9 | Design detailed information medical report page | Complex | 0.5 |
| 3. 10 | Design service list page | Simple | 0.1 |
| 3. 11 | Design show more treatment list page | Simple | 0.1 |
| 3. 12 | Design show more acne prevention list page | Simple | 0.1 |
| 3. 13 | Design show more cause of acne list page | Simple | 0.1 |
| 3. 14 | Design detailed information treatment list page | Medium | 0.2 |
| 3. 15 | Design detailed information acne prevention and cause of acne page | Medium | 0.5 |
| 3. 16 | Design invoice list page | Medium | 0.2 |
| 3. 17 | Design news page | Simple | 0.1 |
| 3. 18 | Design about us page | Simple | 0.1 |
| 3. 19 | Design scan AI detection acne page | Medium | 0.1 |
| 3. 20 | Design home page of the role doctor | Simple | 0.1 |
| 3. 21 | Design appointment page of the role doctor | Simple | 0.1 |
| 3. 22 | Design medical record list page of the role doctor | Simple | 0.1 |
| 3. 23 | Design medical record details page of the role doctor | Simple | 0.1 |
| 3. 24 | Design test result page of the role doctor | Simple | 0.1 |
| 4 | Web service API Skinsense clinic in web-based application |  |  |
| 4. 1 | Create dermatological API service | Medium | 0.1 |
| 4. 2 | Create detail doctor API service | Medium | 0.1 |
| 4. 3 | Create detail specialist API service | Medium | 0.1 |
| 4. 4 | Create invoice API service | Medium | 0.1 |
| 4. 5 | Create medical report service | Medium | 0.1 |
| 4. 6 | Create medication service | Medium | 0.1 |
| 4. 7 | Create role service | Medium | 0.1 |
| 4. 8 | Create role specialist service | Medium | 0.1 |
| 4. 9 | Create room clinic service | Medium | 0.1 |
| 4. 10 | Create account service | Medium | 0.1 |
| 4. 11 | Create appointment service | Medium | 0.1 |
| 4. 12 | Create doctor service | Medium | 0.1 |
| 4. 13 | Create employee service | Medium | 0.1 |
| 4. 14 | Create news service | Medium | 0.1 |
| 4. 15 | Create prescription service | Medium | 0.1 |
| 4. 16 | Create report from AI service | Medium | 0.1 |
| 4. 17 | Create specialist service | Medium | 0.1 |
| 4. 18 | Create patient service | Medium | 0.1 |
| 4. 19 | Create treatment service | Medium | 0.1 |
| 4. 20 | Create room service | Medium | 0.1 |
| 5 | API Authentication in web-based application |  |  |
| 5. 1 | Create JWT token | Medium | 0.25 |
| 5. 2 | Create middleware function | Medium | 0.25 |
| 5. 3 | Logic login - check login information on the web API service | Medium | 0.5 |
| 6 | User Authentication in web-based application |  |  |
| 6. 1 | Logic register user – check validation | Medium | 0.25 |
| 6. 2 | Logic register user – user email and password authentication | Complex | 0.5 |
| 6. 3 | Logic register user –check verify key send to email | Complex | 0.5 |
| 6. 4 | Logic login – check validation | Medium | 0.25 |
| 6. 5 | Logic login user – check login information on database | Medium | 0.25 |
| 6. 6 | Logic logout | Simple | 0.1 |
| 6. 7 | Logic forgot password – check validation | Medium | 0.25 |
| 6. 8 | Logic forgot password – check verify key send to email | Complex | 0.25 |
| 7 | Appointment logic in web-based application |  |  |
| 7. 1 | Create calendar component | Simple | 0.1 |
| 7. 2 | Logic calendar – check validation date and time | Complex | 0.5 |
| 7. 3 | Logic treatment – check validation select item treatment | Complex | 0.5 |
| 7. 4 | Logic appointment date. time - check validation select item treatment | Medium | 0.25 |
| 7. 5 | Logic list of appointment – cancel appointment | Medium | 0.25 |
| 7. 6 | Logic list of appointment – view list of appointment | Medium | 0.25 |
| 7. 7 | Logic list of appointment – view detail appointment | Medium | 0.25 |
| 7. 8 | Logic list of appointment – reschedule appointment | Simple | 0.1 |
| 8 | Medical record logic in web-based application |  |  |
| 8. 1 | Logic list of medical record – details medical record | Medium | 0.25 |
| 8. 2 | Logic details medical record – view details medical record | Medium | 0.25 |
| 9 | Invoice Logic in web-based application |  |  |
| 9. 1 | Logic list of invoices – view invoices | Medium | 0.25 |
| 9. 2 | Logic invoice - checkout invoice | Medium | 0.25 |
| 9. 3 | Logic list of invoices – view details invoice | Medium | 0.25 |
| 9. 4 | Logic invoice status – set status “proceeding”. “paid”. “unpaid”. | Medium | 0.25 |
| 10 | The patients examined logic in web-based application |  |  |
| 10. 1 | Logic list of patients examined – view list of patients examined | Medium | 0.25 |
| 11 | Profile Logic in web-based application |  |  |
| 11. 1 | Logic edits profile user – check validation information profile | Medium | 0.25 |
| 11. 2 | Logic edits profile user – check verify email | Complex | 0.5 |
| 11. 3 | Logic profile user – upload image | Medium | 0.25 |
| 12 | Scan AI detection acne in web-based application |  |  |
| 12. 1 | Logic Scan AI detection acne – upload image skin | Medium | 0.5 |
| 12. 2 | Logic Scan AI detection acne – call API AI to website | Complex | 0.5 |
| 12. 3 | Logic Scan AI detection acne – showing test result | Simple | 0.25 |
| 12. 4 | Logic Scan AI detection acne – store scanned images in the database | Complex | 0.5 |
| 12. 5 | Logic Scan AI detection acne – showing history test image of user | Medium | 0.25 |
| 13 | News Logic in web-base application | Medium | 0.1 |
| 13. 1 | Logic news - Create news | Medium | 0.1 |
| 13. 2 | Logic news - Read news | Medium | 0.1 |
| 13. 3 | Logic news - Update news | Medium | 0.1 |
| 13. 4 | Logic news - Delete news | Medium | 0.1 |
| 14 | RoomClinic Logic in web-base application | Medium | 0.1 |
| 14. 1 | Logic roomClinic - Create roomClinic | Medium | 0.1 |
| 14. 2 | Logic roomClinic - Read roomClinic | Medium | 0.1 |
| 14. 3 | Logic roomClinic - Update roomClinic | Medium | 0.1 |
| 14. 4 | Logic roomClinic - Delete roomClinic | Medium | 0.1 |
| 15 | Treatment Logic in web-base application | Medium | 0.1 |
| 15. 1 | Logic treatment - Create treatment | Medium | 0.1 |
| 15. 2 | Logic treatment - Read treatment | Medium | 0.1 |
| 15. 3 | Logic treatment - Update treatment | Medium | 0.1 |
| 15. 4 | Logic treatment - Delete treatment | Medium | 0.1 |
| 16 | Employee Logic in web-base application | Medium | 0.1 |
| 16. 1 | Logic employee - Create employee | Medium | 0.1 |
| 16. 2 | Logic employee - Read employee | Medium | 0.1 |
| 16. 3 | Logic employee - Update employee | Medium | 0.1 |
| 16. 4 | Logic employee - Delete employee | Medium | 0.1 |
| 17 | Medication Logic in web-base application | Medium | 0.1 |
| 17. 1 | Logic medication - Create medication | Medium | 0.1 |
| 17. 2 | Logic medication - Read medication | Medium | 0.1 |
| 17. 3 | Logic medication - Update medication | Medium | 0.1 |
| 17. 4 | Logic medication - Delete medication | Medium | 0.1 |
| 18 | Patient Logic in web-base application | Medium | 0.1 |
| 18. 1 | Logic patient - Create patient | Medium | 0.1 |
| 18. 2 | Logic patient - Read patient | Medium | 0.1 |
| 18. 3 | Logic patient - Update patient | Medium | 0.1 |
| 18. 4 | Logic patient - Delete patient | Medium | 0.1 |
| 19 | User Authentication in android application |  |  |
| 19. 1 | Logic register user – check validation | Medium | 0.25 |
| 19. 2 | Logic register user – user email and password authentication | Complex | 1 |
| 19. 3 | Logic register user –check verify key send to email | Complex | 0.5 |
| 19. 4 | Logic login – check validation | Medium | 0.25 |
| 19. 5 | Logic login user – check login information on database | Medium | 0.25 |
| 19. 6 | Logic logout | Simple | 0.25 |
| 19. 7 | Logic forgot password – check validation | Medium | 0.25 |
| 19. 8 | Logic forgot password – check verify key send to email | Complex | 0.5 |
| 20 | Appointment logic in android application |  |  |
| 20. 1 | Create calendar component | Simple | 0.1 |
| 20. 2 | Logic calendar – check validation date and time | Medium | 0.1 |
| 20. 3 | Logic treatment – check validation select item treatment | Medium | 0.1 |
| 20. 4 | Logic appointment date. time - check validation select item treatment | Medium | 0.1 |
| 20. 5 | Logic list of appointment – cancel appointment | Medium | 0.1 |
| 20. 6 | Logic list of appointment – view list of appointment | Medium | 0.1 |
| 20. 7 | Logic list of appointment – view detail appointment | Medium | 0.1 |
| 21 | Profile Logic in android application |  |  |
| 21. 1 | Logic edits profile user – check validation information profile | Medium | 0.1 |
| 21. 2 | Logic profile user – check verify email | Medium | 0.1 |
| 21. 3 | Logic profile user – upload image | Simple | 0.1 |
| 22 | Service List in android application |  | 0.1 |
| 22. 1 | Create service list component | Simple | 0.1 |
| 22. 2 | Logic service list – access to database to show information about that service | Medium | 0.1 |
| 23 | Medical record logic in android application |  |  |
| 23.1 | Logic list of medical record – details medical record | Medium | 0.2 |
| 23.1 | Logic details medical record – view details medical record | Medium | 0.2 |
| 23.1 | Logic details medical record – view details test result in medical record | Medium | 0.2 |
| 24 | The patients examined logic in android application |  |  |
| 24. 1 | Logic list of patients examined – view list of patients examined | Medium | 0.25 |
| 25 | Scan AI detection acne in android application |  |  |
| 25. 1 | Logic Scan AI detection acne – upload image skin | Medium | 0.5 |
| 25. 2 | Logic Scan AI detection acne – call API AI to website | Complex | 0.5 |
| 25. 3 | Logic Scan AI detection acne – showing test result | Simple | 0.25 |
| 25. 4 | Logic Scan AI detection acne – store scanned images in the database | Complex | 0.5 |
| 25. 5 | Logic Scan AI detection acne – showing history test image of user | Medium | 0.25 |
| 25. 6 | Logic Scan AI detection acne – configuration camera to scan AI | Complex | 0.5 |
| 25. 7 | Logic Scan AI detection acne – store results after scanning AI to medical record | Complex | 0.5 |
| 26 | Writing report and graph |  |  |
| 26. 1 | Write document report 1 | Medium | 6.5 |
| 26. 2 | Write document report 2 | Medium | 6.5 |
| 26. 3 | Write document report 3 | Medium | 6.5 |
| 26. 4 | Write document report 4 | Medium | 6.5 |
| 26. 5 | Write document report 5 | Medium | 6.5 |
| 26. 6 | Write document report 6 | Medium | 6.5 |
| 26. 7 | Write document report 7 | Complex | 6.5 |
| 26. 8 | Draw diagram | Complex | 6.5 |
|  | Total Estimated Effort (man-days) |  | 90.1 |

### 1.2 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Crash web server | High | High | If the server system crashes, it will lead to the client being unable to use the website and application on a smart phone |
| 2 | Difficult to manage failure even after testing | High | Medium | Inadequate testing could result in software defects and operational issues. |
| 3 | Crash server Cloudinary | Medium | Medium | Crash server Cloudinary will not be able to store the images the user has taken to perform AI scans |
| 4 | Loss of personnel | High | High | During the research phase, this problem will cause little damage in terms of personnel, but if it comes to the middle of the project phase, it will cause a huge loss of personnel and it will be difficult to find a replacement. |

## 2. Management Approach

### 2.1 Project Process

Figure 1. Agile methodology

Meeting: The meeting will gather all members to brainstorm ideas, including topics, which products are aimed at, what technologies to use, and clearly defining the goals.

Plan: After having a specific idea, we will make a time plan and divide it into specific tasks for each member. Each member will be given a different role to focus on successfully completing what they are good at in their field.

Requirement:  Write 7 documents and check the progress once a week.

Develop: Each of the assigned tasks in the plan member will take on tasks when completing a role and have a different specific task.

Test: After completing the assigned tasks, the tester will take on the role of testing the product and, if there is an error, will notify the developer.

Evaluate: The final step is to evaluate the that to ensure product it has met the requirements outlined in the documents.

### 2.2 Quality Management

To improve project quality and achieve project quality objectives for the Dermatology Clinic Management System (DCMS) as an Android and web-based application, a comprehensive quality assurance approach should be implemented. This approach would include various strategies to prevent errors, conduct thorough reviews, and implement rigorous testing at various levels of the development process. Below is a detailed overview of the quality approach:

- Defect Prevention: Establish clear coding standards and guidelines to ensure consistency and readability of the codebase. Conduct regular code reviews to identify and address potential defects and code quality issues before they escalate.

- Unit Testing: Implement unit testing for individual components and modules of the DCMS. Develop a suite of automated unit tests that cover critical functionalities and edge cases to verify the correctness of each unit of code.

- System Testing: Perform comprehensive system testing to validate the entire application's functionality against the specified requirements. Create test scenarios that cover common user workflows, edge cases, and boundary conditions. Implement automated regression testing to ensure that new changes don't introduce unintended side effects.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| C# | TinTT, HungLH, HieuTH, KhaTM, KhangLTV | 01/05/2023 – 01/06/2023 | Mandatory |
| Python | HungLH, KhaTM | 01/05/2023 – 01/06/2023 | Mandatory |
| React | KhaTM | 01/05/2023 – 01/06/2023 | Mandatory |
| React Native | TinTT, KhangLTV | 01/05/2023 – 01/06/2023 | Mandatory |
| Gitlab, source tree | HieuTH | 01/05/2023 – 01/06/2023 | Mandatory |
| Axios | HieuTH, HungLH | 01/05/2023 – 01/06/2023 | Mandatory |
| Draw diagram | KhangLTV, KhaTM | 01/05/2023 – 01/06/2023 | Mandatory |
| Cloudinary | HungLH | 01/05/2023 – 01/06/2023 | Mandatory |

## 3. Master Schedule

| # | Deliverable | Duration | Due Date | Deliverable Scope |
| --- | --- | --- | --- | --- |
| 1 | Project Plan | 90 days | 01/05/2023 – 11/08/2023 |  |
| 2 | Project Start | 0 days | 01/05/2023 |  |
| 3 | Phase 1 – Meeting and Planning |  |  |  |
| 4 | Meeting | 1 day | 01/05/2023 | Define the goal and direction of the application. |
| 5 | Phase 2 – Design Requirements |  |  |  |
| 6 | Prepare report 1 | 5 days | 02/05/2023 – 08/05/2023 |  |
| 7 | Review report 1 and submit | 1 day | 09/05/2023 | Report 1 – Project Introduction |
| 8 | Prepare report 2 | 5 days | 10/05/2023 – 17/05/2023 |  |
| 9 | Review report 2 and submit | 1 day | 18/05/2023 | Report 2 – Project Management Plan |
| 10 | Prepare report 3 | 5 days | 19/05/2023 – 26/05/2023 |  |
| 11 | Review report 3 and submit | 1 day | 27/05/2023 | Report 3 – Software Requirement Specification |
| 12 | Prepare report 4 | 5 days | 28/05/2023 – 04/06/2023 |  |
| 13 | Review report 4 and submit | 1 day | 05/06/2023 | Report 4 – Software Design Document |
| 14 | Phase 3 - Initiation |  |  |  |
| 15 | Design UI/UX for android application | 10 days | 06/06/2023 – 16/06/2023 | UI/UX Android application |
| 16 | Design UI/UX for web application | 10 days | 17/06/2023 – 27/06/2023 | UI/UX web application |
| 17 | Code Iteration 1 | 10 days | 28/06/2023 – 07/07/2023 | API Web Service, Web server |
| 18 | Testing | 25 days | 10/07/2023 – 05/08/2023 |  |
| 19 | Fix bug | 5 days | 09/06/2023 – 14/07/2023 |  |
| 20 | Code Iteration 2 | 10 days | 15/07/2023 – 25/07/2023 | API AI, AI Detection Acne, Web Dermatology Clinic Management System. |
| 21 | Testing | 1 days | 05/06/2023 |  |
| 22 | Fix bug | 5 days | 15/07/2023 – 25/07/2023 |  |
| 23 | Code Iteration 3 | 10 days | 15/07/2023 – 25/07/2023 | Android application Dermatology Clinic Management System. |
| 24 | Testing | 1 days | 05/06/2023 |  |
| 25 | Fix bug | 5 days | 15/07/2023 – 25/07/2023 |  |
| 26 | Phase 4 – Testing | 10 days | 15/07/2023 – 25/07/2023 |  |
| 27 | Testing all system | 5 days | 15/07/2023 – 25/07/2023 | Codes, System test reports |
| 28 | Fix bugs | 5 days | 15/07/2023 – 25/07/2023 |  |
| 29 | Prepare report 5 | 5 days | 15/07/2023 – 25/07/2023 |  |
| 30 | Review report 5 and submit | 1 day | 05/06/2023 | Report5 – Test Documentation |
| 31 | Prepare report 6 | 5 days | 15/07/2023 – 25/07/2023 |  |
| 32 | Review report 6 and submit | 1 day | 05/06/2023 | Report6 – Software User Guides |
| 33 | Prepare for Deployment | 10 days | 15/07/2023 – 25/07/2023 |  |
| 34 | Phase 5 – Evaluate |  |  |  |
| 35 | Clean code | 5 days | 15/07/2023 – 25/07/2023 |  |
| 36 | Fix bugs | 5 days | 15/07/2023 – 25/07/2023 |  |
| 37 | Prepare report 7 | 5 days | 10/05/2023 – 10/08/2023 |  |
| 38 | Review report 7 and submit | 5 days | 10/05/2023 – 10/08/2023 | Report7 – Final Project Report |
| 39 | Deploy Final Package | 5 days | 05/08/2023 – 10/08/2023 | Final Codes & documents, User manual |

## 4. Responsibility Assignments

D~Do; R~Review; S~Support, I~Informed

| Responsibility | HungLH CE150320 | HieuTH CE150749 | KhangLTV CE150092 | KhaTM CE150695 | TinTT CE150623 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | S | R | R | R |
| Define SRS, SDD documents | I | I | I | D | R |
| Design UX/UI | R | D | R | R | D |
| Implement coding | D | D | D | D | D |
| Prepare SDD Document (User Requirements) | I | R | D | I | R |
| Perform Testing | R | R | D | R | R |

## 5. Project Communication

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Teams | HungLH, KhaTM, HieuTH, KhangLTV, TinTT | Transfer information project and brainstorm. | Week 1 | Teams |
| Plan application | HungLH, KhaTM, HieuTH, KhangLTV, TinTT | Task assignment | Week 2 | C#, Database |
| Offline coding | HungLH, KhaTM, HieuTH, KhangLTV, TinTT | Coding full stack | Week 3 – Week 9 | C#, Database, Nginx, Axios |
| Training AI | HungLH, KhaTM, HieuTH, KhangLTV, TinTT | Code and Train AI | Week 3 – week 8 | Python, Cloudinary |
| UI/UX application | HungLH, KhaTM, HieuTH, KhangLTV, TinTT | Design UI/UX | Week 3 – Week 5 | Figma |

## 6. Configuration Management

### 6.1 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Framework | .Net Core 6 |
| Programming language | C#, Linux, Python |
| API | API |
| DBMS | SQL Server |
| IDEs/Editors | Visual Studio Code, Visual Studio, Axios |
| UML tools | Draw.io |
| Version Control | GitLab, Source Tree |
| Deployment server | Nginx Web Service |
| Project management tool | GitLab |

### 6.2 Document Management

- Use Microsoft Word 2019: write report 1-7.

- Draw.io: draw diagrams.

- Document online: Google Sheets

### 6.3 Source Code Management

- Use Visual Studio Code: code android application.

- Use Visual Studio: code web application.

- Use Axios: call API server web application and android application.

- SQL Server: design database.

- GitLab, Source Tree: store code and text files.